## Slide 1
PMP
Project Management Professional (PMP®) Certification Preparation Course
A GUIDE TO:
The Project Management Body Of Knowledge
(PMBOK® Guide) – Sixth Edition
Constructed By:
Samer F. Kamal, PMP
Osama A. AlWazzan
Azam M. Zaqzouq (BCS, MCT, PMP)
PM Consultant & Trainer & Researcher
azam@zaqzouq.com

## Slide 2
Project Management Process Groups and Knowledge Areas
Final Product, Service or Result.
Develop Project Charter
(P1.4.1) [P2.2.1]
Identify Stakeholders (P1.13.1) [P2.2.2]
INITIATING PROCESS GROUP [Part2.2]
Close Project or Phase
(P1.4.7) [P2.6.1]
CLOSING PROCESS GROUP [Part2.6]
FINISH
Monitor and Control Project Work
(P1.4.5) [P2.5.1]
Perform Integrated Change Control
(P1.4.6) [P2.5.2]
Validate Scope
(P1.5.5) [P2.5.3]
Control Quality
(P1.8.3) [P2.5.7]
Monitor Stakeholder Engagement
(P1.13.4) [P2.5.12]
Monitor Communications
(P1.10.3) [P2.5.9]
Control Schedule
(P1.6.6) [P2.5.5]
Control Costs
(P1.7.4) [P2.5.6]
Control Scope
(P1.5.6) [P2.5.4]
Monitor Risks
(P1.11.7) [P2.5.10]
MONITORING & CONTROLLING PROCESS GROUP [Part2.5]
Control Resources
(P1.9.6) [P2.5.8]
Control Procurements
(P1.12.3) [P2.5.11]
Develop Project Management Plan (P1.4.2) [P2.3.1]
Deﬁne Scope
(P1.5.3) [P2.3.4]
Deﬁne Activities
(P1.6.2) [P2.3.7]
Sequence Activities (P1.6.3) [P2.3.8]
Estimate Activity Durations
(P1.6.4) [P2.3.9]
Develop Schedule
(P1.6.5) [P2.3.10]
Collect Requirements (P1.5.2) [P2.3.3]
Estimate Costs
(P1.7.2) [P2.3.12]
Determine Budget
(P1.7.3) [P2.3.13]
Plan Quality Management
(P1.8.1) [P2.3.14]
Plan Resource Management
(P1.9.1) [P2.3.15]
Plan Communications Management
(P1.10.1) [P2.3.17]
Plan Risk Management
(P1.11.1) [P2.3.18]
Identify Risks
(P1.11.2) [P2.3.19]
Plan Risk Responses
(P1.11.5) [P2.3.22]
Plan Stakeholder Engagement
(P1.13.2) [P2.3.24]
Perform Qualitative Risk Analysis
(P1.11.3) [P2.3.20]
Perform Quantitative Risk Analysis
(P1.11.4) [P2.3.21]
Create WBS
(P1.5.4) [P2.3.5]
Plan Scope Management
(P1.5.1) [P2.3.2]
Plan Schedule Management
(P1.6.1) [P2.3.6]
Plan Cost Management
(P1.7.1) [P2.3.11]
Plan Procurement Management
(P1.12.1) [P2.3.23]
Estimate Activity Resources
(P1.9.2) [P2.3.16]
PLANNING PROCESS GROUP [Part2.3]
According to PMI PMBOK® Guide - Sixth Edition
Annotation 5
The arrows portray examples of permutations through interrelationships, interactions, overlaps, iterations, and integration within and among the Project Management Processes and Process Groups.
Annotation 6
In reality, and due to uniqueness of individual projects, the appropriate application and agility of Processes and Process Groups are determined by the Project Management Professional (PMP) through managing/engaging the project stakeholders.
Annotation 7
The Project Management Processes are shown in the Process Group in which most of the related activities take place.
Annotation 8
The Project Management Process Groups are neither project life cycle phases nor stages.
Annotation 1
[P2.X1] Part2: The “Standard” for Project Management.
X1: The Project Management ﬁve (5) Process Groups.
Annotation 2
[P2.Y1.Y2] Part2: The “Standard” for Project Management.
Y1: The Project Management ﬁve (5) Process Groups.
Y2: The Project Management forty-nine (49) Processes.
Annotation 3
(P1.Z1.Z2) Part1: The “Guide” to the Project Management Body of Knowledge (PMBOK® Guide).
Z1: Project Management ten (10) Knowledge Areas sections.
Z2: Project Management Knowledge Areas subsections.
Annotation 4
Among the total of six hundred sixty-ﬁve (665) ITTOs (i.e.; Inputs, Tools & Techniques, and Outputs) only one hundred forty-seven (147) ITTOs are unique.
EXECUTING PROCESS GROUP [Part2.4]
Manage Project Knowledge
(P1.4.4) [P2.4.2]
Direct and Manage Project Work
(P1.4.3) [P2.4.1]
Acquire Resources
(P1.9.3) [P2.4.4]
Develop Team
(P1.9.4) [P2.4.5]
Manage Team
(P1.9.5) [P2.4.6]
Manage Quality
(P1.8.2) [P2.4.3]
Manage Communications
(P1.10.2) [P2.4.7]
Conduct Procurements
(P1.12.2) [P2.4.9]
Manage Stakeholder Engagement
(P1.13.3) [P2.4.10]
Implement Risk Responses
(P1.11.6) [P2.4.8]
HOME
START
PROJECT MANAGEMENT KNOWLEDGE AREAS (P1.4-13)
 | Project Integration Management (P1.4)
 | Project Scope Management (P1.5)
 | Project Schedule Management (P1.6)
 | Project Cost Management (P1.7)
 | Project Quality Management (P1.8)
 | Project Resource Management (P1.9)
 | Project Communications Management (P1.10)
 | Project Risk Management (P1.11)
 | Project Procurement Management (P1.12)
 | Project Stakeholder Management (P1.13)

## Slide 3
Project Management Process Groups and Knowledge Areas
PROJECT MANAGEMENT KNOWLEDGE AREAS (P1.4-13)
Final Product, Service or Result.
Develop Project Charter
(P1.4.1) [P2.2.1]
INITIATING PROCESS GROUP [Part2.2]
Close Project or Phase
(P1.4.7) [P2.6.1]
CLOSING PROCESS GROUP [Part2.6]
 | Project Integration Management (P1.4)
 | Project Scope Management (P1.5)
 | Project Schedule Management (P1.6)
 | Project Cost Management (P1.7)
 | Project Quality Management (P1.8)
 | Project Resource Management (P1.9)
 | Project Communications Management (P1.10)
 | Project Risk Management (P1.11)
 | Project Procurement Management (P1.12)
 | Project Stakeholder Management (P1.13)
FINISH
Monitor and Control Project Work
(P1.4.5) [P2.5.1]
Perform Integrated Change Control
(P1.4.6) [P2.5.2]
MONITORING & CONTROLLING PROCESS GROUP [Part2.5]
Develop Project Management Plan
(P1.4.2) [P2.3.1]
PLANNING PROCESS GROUP [Part2.3]
Annotation 5
The arrows portray examples of permutations through interrelationships, interactions, overlaps, iterations, and integration within and among the Project Management Processes and Process Groups.
Annotation 6
In reality, and due to uniqueness of individual projects, the appropriate application and agility of Processes and Process Groups are determined by the Project Management Professional (PMP) through managing/engaging the project stakeholders.
Annotation 7
The Project Management Processes are shown in the Process Group in which most of the related activities take place.
Annotation 8
The Project Management Process Groups are neither project life cycle phases nor stages.
Annotation 1
[P2.X1] Part2: The “Standard” for Project Management.
X1: The Project Management ﬁve (5) Process Groups.
Annotation 2
[P2.Y1.Y2] Part2: The “Standard” for Project Management.
Y1: The Project Management ﬁve (5) Process Groups.
Y2: The Project Management forty-nine (49) Processes.
Annotation 3
(P1.Z1.Z2) Part1: The “Guide” to the Project Management Body of Knowledge (PMBOK® Guide).
Z1: Project Management ten (10) Knowledge Areas sections.
Z2: Project Management Knowledge Areas subsections.
Annotation 4
Among the total of six hundred sixty-ﬁve (665) ITTOs (i.e.; Inputs, Tools & Techniques, and Outputs) only one hundred forty-seven (147) ITTOs are unique.
EXECUTING PROCESS GROUP [Part2.4]
Manage Project Knowledge
(P1.4.4) [P2.4.2]
Direct and Manage Project Work
(P1.4.3) [P2.4.1]
HOME
START
According to PMI PMBOK® Guide - Sixth Edition

## Slide 4
Project Management Process Groups and Knowledge Areas
Final Product, Service or Result.
INITIATING PROCESS GROUP [Part2.2]
CLOSING PROCESS GROUP [Part2.6]
FINISH
Validate Scope
(P1.5.5) [P2.5.3]
Control Scope
(P1.5.6) [P2.5.4]
MONITORING & CONTROLLING PROCESS GROUP [Part2.5]
Deﬁne Scope
(P1.5.3) [P2.3.4]
Collect Requirements (P1.5.2) [P2.3.3]
Create WBS
(P1.5.4) [P2.3.5]
Plan Scope Management
(P1.5.1) [P2.3.2]
PLANNING PROCESS GROUP [Part2.3]
Annotation 5
The arrows portray examples of permutations through interrelationships, interactions, overlaps, iterations, and integration within and among the Project Management Processes and Process Groups.
Annotation 6
In reality, and due to uniqueness of individual projects, the appropriate application and agility of Processes and Process Groups are determined by the Project Management Professional (PMP) through managing/engaging the project stakeholders.
Annotation 7
The Project Management Processes are shown in the Process Group in which most of the related activities take place.
Annotation 8
The Project Management Process Groups are neither project life cycle phases nor stages.
Annotation 1
[P2.X1] Part2: The “Standard” for Project Management.
X1: The Project Management ﬁve (5) Process Groups.
Annotation 2
[P2.Y1.Y2] Part2: The “Standard” for Project Management.
Y1: The Project Management ﬁve (5) Process Groups.
Y2: The Project Management forty-nine (49) Processes.
Annotation 3
(P1.Z1.Z2) Part1: The “Guide” to the Project Management Body of Knowledge (PMBOK® Guide).
Z1: Project Management ten (10) Knowledge Areas sections.
Z2: Project Management Knowledge Areas subsections.
Annotation 4
Among the total of six hundred sixty-ﬁve (665) ITTOs (i.e.; Inputs, Tools & Techniques, and Outputs) only one hundred forty-seven (147) ITTOs are unique.
EXECUTING PROCESS GROUP [Part2.4]
HOME
START
PROJECT MANAGEMENT KNOWLEDGE AREAS (P1.4-13)
 | Project Integration Management (P1.4)
 | Project Scope Management (P1.5)
 | Project Schedule Management (P1.6)
 | Project Cost Management (P1.7)
 | Project Quality Management (P1.8)
 | Project Resource Management (P1.9)
 | Project Communications Management (P1.10)
 | Project Risk Management (P1.11)
 | Project Procurement Management (P1.12)
 | Project Stakeholder Management (P1.13)
According to PMI PMBOK® Guide - Sixth Edition

## Slide 5
Project Management Process Groups and Knowledge Areas
Final Product, Service or Result.
INITIATING PROCESS GROUP [Part2.2]
FINISH
Control Schedule
(P1.6.6) [P2.5.5]
MONITORING & CONTROLLING PROCESS GROUP [Part2.5]
Deﬁne Activities
(P1.6.2) [P2.3.7]
Sequence Activities
(P1.6.3) [P2.3.8]
Estimate Activity Durations
(P1.6.4) [P2.3.9]
Develop Schedule
(P1.6.5) [P2.3.10]
Plan Schedule Management
(P1.6.1) [P2.3.6]
PLANNING PROCESS GROUP [Part2.3]
Annotation 5
The arrows portray examples of permutations through interrelationships, interactions, overlaps, iterations, and integration within and among the Project Management Processes and Process Groups.
Annotation 6
In reality, and due to uniqueness of individual projects, the appropriate application and agility of Processes and Process Groups are determined by the Project Management Professional (PMP) through managing/engaging the project stakeholders.
Annotation 7
The Project Management Processes are shown in the Process Group in which most of the related activities take place.
Annotation 8
The Project Management Process Groups are neither project life cycle phases nor stages.
Annotation 1
[P2.X1] Part2: The “Standard” for Project Management.
X1: The Project Management ﬁve (5) Process Groups.
Annotation 2
[P2.Y1.Y2] Part2: The “Standard” for Project Management.
Y1: The Project Management ﬁve (5) Process Groups.
Y2: The Project Management forty-nine (49) Processes.
Annotation 3
(P1.Z1.Z2) Part1: The “Guide” to the Project Management Body of Knowledge (PMBOK® Guide).
Z1: Project Management ten (10) Knowledge Areas sections.
Z2: Project Management Knowledge Areas subsections.
Annotation 4
Among the total of six hundred sixty-ﬁve (665) ITTOs (i.e.; Inputs, Tools & Techniques, and Outputs) only one hundred forty-seven (147) ITTOs are unique.
EXECUTING PROCESS GROUP [Part2.4]
HOME
START
CLOSING PROCESS GROUP [Part2.6]
PROJECT MANAGEMENT KNOWLEDGE AREAS (P1.4-13)
 | Project Integration Management (P1.4)
 | Project Scope Management (P1.5)
 | Project Schedule Management (P1.6)
 | Project Cost Management (P1.7)
 | Project Quality Management (P1.8)
 | Project Resource Management (P1.9)
 | Project Communications Management (P1.10)
 | Project Risk Management (P1.11)
 | Project Procurement Management (P1.12)
 | Project Stakeholder Management (P1.13)
According to PMI PMBOK® Guide - Sixth Edition

## Slide 6
Project Management Process Groups and Knowledge Areas
Final Product, Service or Result.
INITIATING PROCESS GROUP [Part2.2]
CLOSING PROCESS GROUP [Part2.6]
FINISH
Control Costs
(P1.7.4) [P2.5.6]
MONITORING & CONTROLLING PROCESS GROUP [Part2.5]
Estimate Costs
(P1.7.2) [P2.3.12]
Determine Budget
(P1.7.3) [P2.3.13]
Plan Cost Management
(P1.7.1) [P2.3.11]
PLANNING PROCESS GROUP [Part2.3]
Annotation 5
The arrows portray examples of permutations through interrelationships, interactions, overlaps, iterations, and integration within and among the Project Management Processes and Process Groups.
Annotation 6
In reality, and due to uniqueness of individual projects, the appropriate application and agility of Processes and Process Groups are determined by the Project Management Professional (PMP) through managing/engaging the project stakeholders.
Annotation 7
The Project Management Processes are shown in the Process Group in which most of the related activities take place.
Annotation 8
The Project Management Process Groups are neither project life cycle phases nor stages.
Annotation 1
[P2.X1] Part2: The “Standard” for Project Management.
X1: The Project Management ﬁve (5) Process Groups.
Annotation 2
[P2.Y1.Y2] Part2: The “Standard” for Project Management.
Y1: The Project Management ﬁve (5) Process Groups.
Y2: The Project Management forty-nine (49) Processes.
Annotation 3
(P1.Z1.Z2) Part1: The “Guide” to the Project Management Body of Knowledge (PMBOK® Guide).
Z1: Project Management ten (10) Knowledge Areas sections.
Z2: Project Management Knowledge Areas subsections.
Annotation 4
Among the total of six hundred sixty-ﬁve (665) ITTOs (i.e.; Inputs, Tools & Techniques, and Outputs) only one hundred forty-seven (147) ITTOs are unique.
EXECUTING PROCESS GROUP [Part2.4]
HOME
START
PROJECT MANAGEMENT KNOWLEDGE AREAS (P1.4-13)
 | Project Integration Management (P1.4)
 | Project Scope Management (P1.5)
 | Project Schedule Management (P1.6)
 | Project Cost Management (P1.7)
 | Project Quality Management (P1.8)
 | Project Resource Management (P1.9)
 | Project Communications Management (P1.10)
 | Project Risk Management (P1.11)
 | Project Procurement Management (P1.12)
 | Project Stakeholder Management (P1.13)
According to PMI PMBOK® Guide - Sixth Edition

## Slide 7
Project Management Process Groups and Knowledge Areas
Final Product, Service or Result.
INITIATING PROCESS GROUP [Part2.2]
CLOSING PROCESS GROUP [Part2.6]
FINISH
Control Quality
(P1.8.3) [P2.5.7]
MONITORING & CONTROLLING PROCESS GROUP [Part2.5]
Plan Quality Management
(P1.8.1) [P2.3.14]
PLANNING PROCESS GROUP [Part2.3]
Annotation 5
The arrows portray examples of permutations through interrelationships, interactions, overlaps, iterations, and integration within and among the Project Management Processes and Process Groups.
Annotation 6
In reality, and due to uniqueness of individual projects, the appropriate application and agility of Processes and Process Groups are determined by the Project Management Professional (PMP) through managing/engaging the project stakeholders.
Annotation 7
The Project Management Processes are shown in the Process Group in which most of the related activities take place.
Annotation 8
The Project Management Process Groups are neither project life cycle phases nor stages.
Annotation 1
[P2.X1] Part2: The “Standard” for Project Management.
X1: The Project Management ﬁve (5) Process Groups.
Annotation 2
[P2.Y1.Y2] Part2: The “Standard” for Project Management.
Y1: The Project Management ﬁve (5) Process Groups.
Y2: The Project Management forty-nine (49) Processes.
Annotation 3
(P1.Z1.Z2) Part1: The “Guide” to the Project Management Body of Knowledge (PMBOK® Guide).
Z1: Project Management ten (10) Knowledge Areas sections.
Z2: Project Management Knowledge Areas subsections.
Annotation 4
Among the total of six hundred sixty-ﬁve (665) ITTOs (i.e.; Inputs, Tools & Techniques, and Outputs) only one hundred forty-seven (147) ITTOs are unique.
EXECUTING PROCESS GROUP [Part2.4]
Manage Quality
(P1.8.2) [P2.4.3]
HOME
START
PROJECT MANAGEMENT KNOWLEDGE AREAS (P1.4-13)
 | Project Integration Management (P1.4)
 | Project Scope Management (P1.5)
 | Project Schedule Management (P1.6)
 | Project Cost Management (P1.7)
 | Project Quality Management (P1.8)
 | Project Resource Management (P1.9)
 | Project Communications Management (P1.10)
 | Project Risk Management (P1.11)
 | Project Procurement Management (P1.12)
 | Project Stakeholder Management (P1.13)
According to PMI PMBOK® Guide - Sixth Edition

## Slide 8
Project Management Process Groups and Knowledge Areas
Final Product, Service or Result.
INITIATING PROCESS GROUP [Part2.2]
CLOSING PROCESS GROUP [Part2.6]
FINISH
MONITORING & CONTROLLING PROCESS GROUP [Part2.5]
Control Resources
(P1.9.6) [P2.5.8]
Plan Resource Management
(P1.9.1) [P2.3.15]
Estimate Activity Resources
(P1.9.2) [P2.3.16]
PLANNING PROCESS GROUP [Part2.3]
Annotation 5
The arrows portray examples of permutations through interrelationships, interactions, overlaps, iterations, and integration within and among the Project Management Processes and Process Groups.
Annotation 6
In reality, and due to uniqueness of individual projects, the appropriate application and agility of Processes and Process Groups are determined by the Project Management Professional (PMP) through managing/engaging the project stakeholders.
Annotation 7
The Project Management Processes are shown in the Process Group in which most of the related activities take place.
Annotation 8
The Project Management Process Groups are neither project life cycle phases nor stages.
Annotation 1
[P2.X1] Part2: The “Standard” for Project Management.
X1: The Project Management ﬁve (5) Process Groups.
Annotation 2
[P2.Y1.Y2] Part2: The “Standard” for Project Management.
Y1: The Project Management ﬁve (5) Process Groups.
Y2: The Project Management forty-nine (49) Processes.
Annotation 3
(P1.Z1.Z2) Part1: The “Guide” to the Project Management Body of Knowledge (PMBOK® Guide).
Z1: Project Management ten (10) Knowledge Areas sections.
Z2: Project Management Knowledge Areas subsections.
Annotation 4
Among the total of six hundred sixty-ﬁve (665) ITTOs (i.e.; Inputs, Tools & Techniques, and Outputs) only one hundred forty-seven (147) ITTOs are unique.
EXECUTING PROCESS GROUP [Part2.4]
Acquire Resources
(P1.9.3) [P2.4.4]
Develop Team
(P1.9.4) [P2.4.5]
Manage Team
(P1.9.5) [P2.4.6]
HOME
START
PROJECT MANAGEMENT KNOWLEDGE AREAS (P1.4-13)
 | Project Integration Management (P1.4)
 | Project Scope Management (P1.5)
 | Project Schedule Management (P1.6)
 | Project Cost Management (P1.7)
 | Project Quality Management (P1.8)
 | Project Resource Management (P1.9)
 | Project Communications Management (P1.10)
 | Project Risk Management (P1.11)
 | Project Procurement Management (P1.12)
 | Project Stakeholder Management (P1.13)
According to PMI PMBOK® Guide - Sixth Edition

## Slide 9
Project Management Process Groups and Knowledge Areas
Final Product, Service or Result.
INITIATING PROCESS GROUP [Part2.2]
CLOSING PROCESS GROUP [Part2.6]
FINISH
Monitor Communications
(P1.10.3) [P2.5.9]
MONITORING & CONTROLLING PROCESS GROUP [Part2.5]
Plan Communications Management
(P1.10.1) [P2.3.17]
PLANNING PROCESS GROUP [Part2.3]
Annotation 5
The arrows portray examples of permutations through interrelationships, interactions, overlaps, iterations, and integration within and among the Project Management Processes and Process Groups.
Annotation 6
In reality, and due to uniqueness of individual projects, the appropriate application and agility of Processes and Process Groups are determined by the Project Management Professional (PMP) through managing/engaging the project stakeholders.
Annotation 7
The Project Management Processes are shown in the Process Group in which most of the related activities take place.
Annotation 8
The Project Management Process Groups are neither project life cycle phases nor stages.
Annotation 1
[P2.X1] Part2: The “Standard” for Project Management.
X1: The Project Management ﬁve (5) Process Groups.
Annotation 2
[P2.Y1.Y2] Part2: The “Standard” for Project Management.
Y1: The Project Management ﬁve (5) Process Groups.
Y2: The Project Management forty-nine (49) Processes.
Annotation 3
(P1.Z1.Z2) Part1: The “Guide” to the Project Management Body of Knowledge (PMBOK® Guide).
Z1: Project Management ten (10) Knowledge Areas sections.
Z2: Project Management Knowledge Areas subsections.
Annotation 4
Among the total of six hundred sixty-ﬁve (665) ITTOs (i.e.; Inputs, Tools & Techniques, and Outputs) only one hundred forty-seven (147) ITTOs are unique.
EXECUTING PROCESS GROUP [Part2.4]
Manage Communications
(P1.10.2) [P2.4.7]
HOME
START
PROJECT MANAGEMENT KNOWLEDGE AREAS (P1.4-13)
 | Project Integration Management (P1.4)
 | Project Scope Management (P1.5)
 | Project Schedule Management (P1.6)
 | Project Cost Management (P1.7)
 | Project Quality Management (P1.8)
 | Project Resource Management (P1.9)
 | Project Communications Management (P1.10)
 | Project Risk Management (P1.11)
 | Project Procurement Management (P1.12)
 | Project Stakeholder Management (P1.13)
According to PMI PMBOK® Guide - Sixth Edition

## Slide 10
Project Management Process Groups and Knowledge Areas
Final Product, Service or Result.
INITIATING PROCESS GROUP [Part2.2]
CLOSING PROCESS GROUP [Part2.6]
FINISH
Monitor Risks
(P1.11.7) [P2.5.10]
MONITORING & CONTROLLING PROCESS GROUP [Part2.5]
Plan Risk Management
(P1.11.1) [P2.3.18]
Identify Risks
(P1.11.2) [P2.3.19]
Plan Risk Responses
(P1.11.5) [P2.3.22]
Perform Qualitative Risk Analysis
(P1.11.3) [P2.3.20]
Perform Quantitative Risk Analysis
(P1.11.4) [P2.3.21]
PLANNING PROCESS GROUP [Part2.3]
Annotation 5
The arrows portray examples of permutations through interrelationships, interactions, overlaps, iterations, and integration within and among the Project Management Processes and Process Groups.
Annotation 6
In reality, and due to uniqueness of individual projects, the appropriate application and agility of Processes and Process Groups are determined by the Project Management Professional (PMP) through managing/engaging the project stakeholders.
Annotation 7
The Project Management Processes are shown in the Process Group in which most of the related activities take place.
Annotation 8
The Project Management Process Groups are neither project life cycle phases nor stages.
Annotation 1
[P2.X1] Part2: The “Standard” for Project Management.
X1: The Project Management ﬁve (5) Process Groups.
Annotation 2
[P2.Y1.Y2] Part2: The “Standard” for Project Management.
Y1: The Project Management ﬁve (5) Process Groups.
Y2: The Project Management forty-nine (49) Processes.
Annotation 3
(P1.Z1.Z2) Part1: The “Guide” to the Project Management Body of Knowledge (PMBOK® Guide).
Z1: Project Management ten (10) Knowledge Areas sections.
Z2: Project Management Knowledge Areas subsections.
Annotation 4
Among the total of six hundred sixty-ﬁve (665) ITTOs (i.e.; Inputs, Tools & Techniques, and Outputs) only one hundred forty-seven (147) ITTOs are unique.
EXECUTING PROCESS GROUP [Part2.4]
Implement Risk Responses
(P1.11.6) [P2.4.8]
HOME
START
PROJECT MANAGEMENT KNOWLEDGE AREAS (P1.4-13)
 | Project Integration Management (P1.4)
 | Project Scope Management (P1.5)
 | Project Schedule Management (P1.6)
 | Project Cost Management (P1.7)
 | Project Quality Management (P1.8)
 | Project Resource Management (P1.9)
 | Project Communications Management (P1.10)
 | Project Risk Management (P1.11)
 | Project Procurement Management (P1.12)
 | Project Stakeholder Management (P1.13)
According to PMI PMBOK® Guide - Sixth Edition

## Slide 11
Project Management Process Groups and Knowledge Areas
Final Product, Service or Result.
INITIATING PROCESS GROUP [Part2.2]
CLOSING PROCESS GROUP [Part2.6]
FINISH
MONITORING & CONTROLLING PROCESS GROUP [Part2.5]
Control Procurements
(P1.12.3) [P2.5.11]
Plan Procurement Management
(P1.12.1) [P2.3.23]
PLANNING PROCESS GROUP [Part2.3]
Annotation 5
The arrows portray examples of permutations through interrelationships, interactions, overlaps, iterations, and integration within and among the Project Management Processes and Process Groups.
Annotation 6
In reality, and due to uniqueness of individual projects, the appropriate application and agility of Processes and Process Groups are determined by the Project Management Professional (PMP) through managing/engaging the project stakeholders.
Annotation 7
The Project Management Processes are shown in the Process Group in which most of the related activities take place.
Annotation 8
The Project Management Process Groups are neither project life cycle phases nor stages.
Annotation 1
[P2.X1] Part2: The “Standard” for Project Management.
X1: The Project Management ﬁve (5) Process Groups.
Annotation 2
[P2.Y1.Y2] Part2: The “Standard” for Project Management.
Y1: The Project Management ﬁve (5) Process Groups.
Y2: The Project Management forty-nine (49) Processes.
Annotation 3
(P1.Z1.Z2) Part1: The “Guide” to the Project Management Body of Knowledge (PMBOK® Guide).
Z1: Project Management ten (10) Knowledge Areas sections.
Z2: Project Management Knowledge Areas subsections.
Annotation 4
Among the total of six hundred sixty-ﬁve (665) ITTOs (i.e.; Inputs, Tools & Techniques, and Outputs) only one hundred forty-seven (147) ITTOs are unique.
EXECUTING PROCESS GROUP [Part2.4]
Conduct Procurements
(P1.12.2) [P2.4.9]
HOME
START
PROJECT MANAGEMENT KNOWLEDGE AREAS (P1.4-13)
 | Project Integration Management (P1.4)
 | Project Scope Management (P1.5)
 | Project Schedule Management (P1.6)
 | Project Cost Management (P1.7)
 | Project Quality Management (P1.8)
 | Project Resource Management (P1.9)
 | Project Communications Management (P1.10)
 | Project Risk Management (P1.11)
 | Project Procurement Management (P1.12)
 | Project Stakeholder Management (P1.13)
According to PMI PMBOK® Guide - Sixth Edition

## Slide 12
Project Management Process Groups and Knowledge Areas
Final Product, Service or Result.
Identify Stakeholders
(P1.13.1) [P2.2.2]
INITIATING PROCESS GROUP [Part2.2]
CLOSING PROCESS GROUP [Part2.6]
FINISH
Monitor Stakeholder Engagement
(P1.13.4) [P2.5.12]
MONITORING & CONTROLLING PROCESS GROUP [Part2.5]
Plan Stakeholder Engagement
(P1.13.2) [P2.3.24]
PLANNING PROCESS GROUP [Part2.3]
Annotation 5
The arrows portray examples of permutations through interrelationships, interactions, overlaps, iterations, and integration within and among the Project Management Processes and Process Groups.
Annotation 6
In reality, and due to uniqueness of individual projects, the appropriate application and agility of Processes and Process Groups are determined by the Project Management Professional (PMP) through managing/engaging the project stakeholders.
Annotation 7
The Project Management Processes are shown in the Process Group in which most of the related activities take place.
Annotation 8
The Project Management Process Groups are neither project life cycle phases nor stages.
Annotation 1
[P2.X1] Part2: The “Standard” for Project Management.
X1: The Project Management ﬁve (5) Process Groups.
Annotation 2
[P2.Y1.Y2] Part2: The “Standard” for Project Management.
Y1: The Project Management ﬁve (5) Process Groups.
Y2: The Project Management forty-nine (49) Processes.
Annotation 3
(P1.Z1.Z2) Part1: The “Guide” to the Project Management Body of Knowledge (PMBOK® Guide).
Z1: Project Management ten (10) Knowledge Areas sections.
Z2: Project Management Knowledge Areas subsections.
Annotation 4
Among the total of six hundred sixty-ﬁve (665) ITTOs (i.e.; Inputs, Tools & Techniques, and Outputs) only one hundred forty-seven (147) ITTOs are unique.
EXECUTING PROCESS GROUP [Part2.4]
Manage Stakeholder Engagement
(P1.13.3) [P2.4.10]
HOME
START
PROJECT MANAGEMENT KNOWLEDGE AREAS (P1.4-13)
 | Project Integration Management (P1.4)
 | Project Scope Management (P1.5)
 | Project Schedule Management (P1.6)
 | Project Cost Management (P1.7)
 | Project Quality Management (P1.8)
 | Project Resource Management (P1.9)
 | Project Communications Management (P1.10)
 | Project Risk Management (P1.11)
 | Project Procurement Management (P1.12)
 | Project Stakeholder Management (P1.13)
According to PMI PMBOK® Guide - Sixth Edition

## Slide 13
THANK YOU FOR
YOUR KIND
ATTENTION
AZAM M. ZAQZOUQ